## Risk Register
Risk ID | Cloud Asset | Risk Description | Likelihood Score | Impact Score | Risk Level | Mitigation | Risk Owner | Status | Evidence | Control Reference | Target Date | Residual Risk
R-001 | Cloud Storage | Storage is publicly accessible | 4 | 5 | Critical | Disable public access and review permissions | Cloud Administrator | Open | Access setting screenshot | NIST CSF 2.0 - PR.DS | 2026-09-14 | Medium
R-002 | Cloud Identity | Administrator accounts do not use MFA | 4 | 5 | Critical | Enable MFA for all administrator accounts | Identity Administrator | Open | MFA status report | NIST CSF 2.0 - PR.AA | 2026-09-14 | Medium
R-003 | Cloud Database | Sensitive data is not encrypted at rest | 3 | 5 | High | Enable encryption at rest and manage encryption keys | Database Administrator | Open | Encryption settings screenshot | NIST CSF 2.0 - PR.DS | 2026-10-07 | Low
R-004 | Cloud Backup | Cloud backups are not regularly tested | 3 | 4 | High | Schedule backups and test data restoration | IT Operations Manager | Open | Backup and restore test report | NIST CSF 2.0 - RC.RP | 2026-10-07 | Medium
R-005 | Cloud IAM | Users have excessive access permissions | 4 | 5 | Critical | Apply least privilege and review user roles | Identity Administrator | Open | User access review report | NIST CSF 2.0 - PR.AA | 2026-09-14 | Medium
R-006 | Cloud Monitoring | Security logging and monitoring are disabled | 4 | 4 | High | Enable security logs and continuous monitoring | Security Operations Manager | Open | Logging configuration screenshot | NIST CSF 2.0 - DE.CM | 2026-10-07 | Medium
R-007 | Cloud Virtual Machines | Virtual machines are not regularly patched | 4 | 4 | High | Implement a monthly patch management process | Cloud Administrator | Open | Patch compliance report | NIST CSF 2.0 - PR.PS | 2026-10-07 | Medium
R-008 | Cloud Data | Sensitive data is not classified | 3 | 4 | High | Classify data and apply sensitivity labels | Data Protection Officer | Open | Data classification report | NIST CSF 2.0 - PR.DS | 2026-10-07 | Low
R-009 | Cloud Records | Data retention policies are not defined | 3 | 3 | Medium | Define and implement data retention policies | Compliance Manager | Open | Approved retention policy | NIST CSF 2.0 - GV.PO | 2026-11-06 | Low
R-010 | Cloud Identity | Inactive user accounts remain enabled | 3 | 4 | High | Disable inactive accounts and perform quarterly reviews | Identity Administrator | Open | Inactive accounts report | NIST CSF 2.0 - PR.AA | 2026-10-07 | Low
R-011 | Cloud Incident Response | No cloud incident response plan exists | 3 | 5 | High | Create and test a cloud incident response plan | Security Manager | Open | Incident response test report | NIST CSF 2.0 - RS.MA | 2026-10-07 | Medium
R-012 | Third-Party Access | Third-party access is not regularly reviewed | 3 | 4 | High | Review third-party access and remove unnecessary permissions | Vendor Risk Manager | Open | Third-party access review report | NIST CSF 2.0 - GV.SC | 2026-10-07 | Medium

## Risk Scoring
Likelihood Level | Likelihood Score | Impact Level | Impact Score | Minimum Score | Risk Rating
Rare | 1 | Insignificant | 1 | 1 | Low
Unlikely | 2 | Minor | 2 | 5 | Medium
Possible | 3 | Moderate | 3 | 10 | High
Likely | 4 | Major | 4 | 17 | Critical
Almost Certain | 5 | Severe | 5

## Dashboard
Cloud Compliance Risk Dashboard
Total Risks | 12 | Risk Level | Count
Critical Risks | 3 | Critical | 3
High Risks | 8 | High | 8
Medium Risks | 1 | Medium | 1
Open Risks | 12
Key Findings
3 critical risks require immediate action
8 high risks require remediation within 30 days
All 12 identified risks are currently open
Priority Actions
1. Restrict public access to cloud storage
2. Enable MFA for administrator accounts
3. Apply least privilege to user permissions
4. Monitor remediation and collect evidence

## Project Overview
Cloud Compliance Risk Assessment
Project Type | Simulated Portfolio Project
Scenario | A fictional company uses cloud services to store data and operate business systems
Objective | Identify, assess, prioritize, and monitor cloud compliance risks
Framework | NIST Cybersecurity Framework 2.0
Scope | Cloud identity, storage, databases, monitoring, backups, and third-party access
Tools | Excel-compatible spreadsheet and Microsoft Learn
Role | Cloud Compliance Analyst
Deliverables | Risk register, risk scoring model, dashboard, findings, and remediation actions
Disclaimer | This is a simulated project created for learning and portfolio purposes
Reference Source | https://www.nist.gov/cyberframework

## Evidence Tracker
Evidence ID | Risk ID | Evidence Name | Evidence Owner | Requested Date | Received Date | Review Status | Reviewer Notes
E-001 | R-001 | Access setting screenshot | Cloud Administrator | 2026-09-08 |  | Pending | Awaiting evidence
E-002 | R-002 | MFA status report | Identity Administrator | 2026-09-08 |  | Pending | Awaiting evidence
E-003 | R-003 | Encryption settings screenshot | Database Administrator | 2026-09-08 |  | Pending | Awaiting evidence
E-004 | R-004 | Backup and restore test report | IT Operations Manager | 2026-09-08 |  | Pending | Awaiting evidence
E-005 | R-005 | User access review report | Identity Administrator | 2026-09-08 |  | Pending | Awaiting evidence
E-006 | R-006 | Logging configuration screenshot | Security Operations Manager | 2026-09-08 |  | Pending | Awaiting evidence
E-007 | R-007 | Patch compliance report | Cloud Administrator | 2026-09-08 |  | Pending | Awaiting evidence
E-008 | R-008 | Data classification report | Data Protection Officer | 2026-09-08 |  | Pending | Awaiting evidence
E-009 | R-009 | Approved retention policy | Compliance Manager | 2026-09-08 |  | Pending | Awaiting evidence
E-010 | R-010 | Inactive accounts report | Identity Administrator | 2026-09-08 |  | Pending | Awaiting evidence
E-011 | R-011 | Incident response test report | Security Manager | 2026-09-08 |  | Pending | Awaiting evidence
E-012 | R-012 | Third-party access review report | Vendor Risk Manager | 2026-09-08 |  | Pending | Awaiting evidence